## First version
Insert variables
N - Number of documents | 1000
G - Number of groups | 20
Number of SME | 1
Hours of SME available in a day | 6
Total SME hours per day | 6
Hours of DA available in a day | 6
Complexity for ML | High
DA tagging time per document, sec | 180
DA splitting time per document, sec | 0
DA OCR quality check time per doc, sec | 40
n - Number of documents from a single group per iteration | 5
Estimation |  |  |  | Average workload during the tagging
Stages | Estimated Days of Work |  |  | DA |  | SME
| DA | SME |  | 65.88% |  | 81.51%
Use Case Analysis | 3 | 0
Qualification | 2 | 1 |  | Number of blocked days
Total days for tagging | 12 | 9 |  | DA |  | SME
Results analysis and report preparation | 2 | 0 |  | 0 |  | 0
TOTAL DAYS | 19 | 10
Expected Productivity
C (expected number of OCR quality check iterations based on documents quality) | 3
A (Coefficient of acceleration based on documents quality) | 1.1
SME 1st iteration tagging time per document | 270 | 1.5 times longer than DA taging
SME 2nd iteration tagging time per document | 245.4545 | A times faster than previous
SME 3rd teration tagging time per document | 223.1405 | A times faster than previous
SME 4th teration tagging time per document | 202.855 | A times faster than previous
SME 5th teration tagging time per document | 184.4136 | A times faster than previous
SME 6th teration tagging time per document | 167.6488 | A times faster than previous
SME 7th teration tagging time per document | 152.408 | A times faster than previous
SME 8th teration tagging time per document | 138.5527 | A times faster than previous
DA 1st iteration validation time per document | 163.6364 | A times faster than DA taging
DA 2nd iteration validation time per document | 148.7603 | A times faster than previous
DA 3rd iteration validation time per document | 135.2367 | A times faster than previous
DA 4rd iteration validation time per document | 122.9424 | A times faster than previous
DA 5rd iteration validation time per document | 111.7658 | A times faster than previous
DA 6rd iteration validation time per document | 101.6053 | A times faster than previous
DA 7rd iteration validation time per document | 92.3685 | A times faster than previous
DA 8rd iteration validation time per document | 83.9713 | A times faster than previous
DA validation of Test Set | 163.6364 | Equal to 1st iteration time
I (Expected number of Tagging Iterations) | 8
Expected Effort per Stage | (hours) | Check | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Day 43 | Day 44 | Day 45 | Day 46 | Day 47 | Day 48 | Day 49 | Day 50
Splitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OCR quality check (C times) | 6.6667 | 6.6667 | 6 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st Iteration (Tagging) | 7.5 | 7.5 | blocked | 6 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd Iteration (Tagging) | 6.8182 | 6.8182 | blocked | blocked | 4.5 | 2.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3rd Iteration (Tagging) | 6.1983 | 6.1983 | blocked | blocked | blocked | blocked | 6 | 0.19835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4th Iteration (Tagging) | 5.6349 | 5.6349 | blocked | blocked | blocked | blocked | blocked | 5.6349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5th Iteration (Tagging) | 5.1226 | 5.1226 | blocked | blocked | blocked | blocked | blocked | blocked | 5.1226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6th Iteration (Tagging) | 4.6569 | 4.6569 | blocked | blocked | blocked | blocked | blocked | blocked | blocked | 4.6569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7th Iteration (Tagging) | 4.2336 | 4.2336 | blocked | blocked | blocked | blocked | blocked | blocked | blocked | blocked | 4.2336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8th Iteration (Tagging) | 3.8487 | 3.8487 | blocked | blocked | blocked | blocked | blocked | blocked | blocked | blocked | blocked | 3.8487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Initial Training Set Tagging (DA) | 5 | 5 | blocked | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st Iteration (Validation) | 4.5455 | 4.5455 | blocked | blocked | 4.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2nd Iteration (Validation) | 4.1322 | 4.1322 | blocked | blocked | blocked | 4.1322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3rd Iteration (Validation) | 3.7566 | 3.7566 | blocked | blocked | blocked | blocked | 3.7566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4th Iteration (Validation) | 3.4151 | 3.4151 | blocked | blocked | blocked | blocked | blocked | 3.4151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5th Iteration (Validation) | 3.1046 | 3.1046 | blocked | blocked | blocked | blocked | blocked | blocked | 3.1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6th Iteration (Validation) | 2.8224 | 2.8224 | blocked | blocked | blocked | blocked | blocked | blocked | blocked | 2.8224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7th Iteration (Validation) | 2.5658 | 2.5658 | blocked | blocked | blocked | blocked | blocked | blocked | blocked | blocked | 2.5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8th Iteration (Validation) | 2.3325 | 2.3325 | blocked | blocked | blocked | blocked | blocked | blocked | blocked | blocked | blocked | 2.3325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test Set Tagging (DA) | 9.0909 | 9.0909 | blocked |  | blocked | blocked | blocked | blocked | blocked | blocked | blocked | blocked | 6 | 3.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SME time | 0 | 6 | 6 | 2.3182 | 6 | 5.8332 | 5.1226 | 4.6569 | 4.2336 | 3.8487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DA time | 6 | 5.6667 | 4.5455 | 4.1322 | 3.7566 | 3.4151 | 3.1046 | 2.8224 | 2.5658 | 2.3325 | 6 | 3.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total SME time for tagging | 44.0131 |  | Day 1: If SME or DA is blocked in between working days, sum for this day is equal to 0.01
Total DA time for tagging | 47.4322
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: You may enter approximate value (e.g. number of suppliers) if you don't know the distribution by groups yet, but DA is expected to identify it in future. If G is too big or cannot be identified at all (i.e. it’s impossible to split documents into real visual groups, because there is a huge variety of templates or no any template at all), set it to be equal to 10 - groups will be formed randomly as 10% of N in each.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - Insert 0 if docs are already split - Insert 30 if time is unknown
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert 30 if time is unknown
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will be calculated automatically as n = N/G/10 If you change it, recommended to use number, which meets the following: n * G * 10 = N

## Complexity legend
Complexity | C | A | I | Description
| (expected number of OCR quality check iterations based on documents quality) | (Coefficient of acceleration based on documents quality) | (Expected number of Tagging Iterations)
Low | 1 | 1.5 | 4 | (all the following is true): High quality original documents (searchable PDF, converted Excel or Word file or Email), high expected OCR quality, stable xml structure across a group, small number of fields (up to 10), fields are not complex (approximately 5 short tokens in one, i.e. dates, numbers, money amounts, very short free text (approximately 5 words))
Medium | 2 | 1.25 | 6 | (all the following is true): Medium or high quality original documents (non-searchable PDF or images with normal resolution, no bar-codes, stamps or handwritten text over the fields), normal OCR quality, but with minor OCR issues expected, number of fields is up to 15 fields are not complex (approximately 5 short tokens in one, i.e. dates, numbers, money amounts, very short free text (approximately 5 words))
High | 3 | 1.1 | 8 | Low, medium or high quality documents, Too many groups, so that one group contains less than 20 documents bad OCR quality, with many OCR mistakes expected, unstable xml structure huge number of fields (more than 15), contains complex fields (very long, with many tokens inside)