## Slide 1: ABC: Trades reconciliation POC
January 19, 2018

## Slide 2: Agenda
Project objectives and scope
Teams’ introduction and structure
Project plan
Next steps

## Slide 3
Project objectives and scope

## Slide 4: Objectives
Demonstrate the potential for automating a significant part of Trades reconciliation process
Prove cognitive automation capabilities for data extraction out of Trades term sheets

## Slide 5: Trades reconciliation process
Monitor mailbox
S
E
Classify emails
No
Yes
Match?
Separate attachment from email
Checker step to validate data
Reconciliation with trades database
Review reconciliation
No
Yes
Send email to middle-office highlighting discrepancies
Trades DB
Robotic bot
Cognitive bot
Manual step
Send confirmation emails
Is Trade?
Trade data extraction

## Slide 6: Deliverables
Robotic bot to separate attachments from the email if any, or body of the email otherwise
Cognitive bot to extract data from machine-typed Trades (email body); rule-based extraction for excel attachments
Manual task – checker step to validate data automatically extracted by cognitive bot
Robotic bot to reconcile data against DB (rules-based reconciliation)
Manual task – checker step to validate reconciliation
Robotic bot to send emails to middle office (confirmation or alert on the deal)

## Slide 7: Success criteria
For fields appearing in documents more than 25% of the time:
  on average, more than 90% accuracy, excluding errors due to OCR conversion
  on average, more than 50% automation rate
Execution of robotic bot(s) for non-exceptional scenarios where the inputs are valid and the business applications are not triggering any processing errors
Manual tasks permitting to add missed or correct wrong machine extracted data and then verifying the data with rules-based reconciliation.

## Slide 8
Teams’ introduction and structure

## Slide 9: Customer team
Antonio
Project Sponsor
Emily
Business User
John
Busienss User
Max
Process Leader
Samantha
Project Lead
Business Unit
IT
Carl
VP Enterprise Alliance
Frances
System Engineer

## Slide 10: Vendor team
Dennis
Account manager
Kelsey
Delivery Manager
Sujith
Executive Sponsor
Carmen
DA
Grorge
RPA Dev / MLE
Mary
RPA Dev
Stephen
RPA Dev
Sam
IT/architecture Support
Julia
Architecture Support

## Slide 11: Customer – roles & responsibilities
Account oversight
Escalation for all account issues
Antonio, Treasury VP
Sr. Responsible Owner
Samantha, Treasury Operations
Main point of contact for Vendor
Identify opportunities for automation at ABC
Project Lead/Process Analyst
Frances, System Engineer
Customer oversight of Tech solutions
Advice & help regarding IT issues
Main point of contact related to IT questions
Systems / Developer
Steering Group
Antonio, Treasury VP
Kim, Sr. Director Internal Audit
Carl, VP Enterprise Alliance

## Slide 12: Vendor – roles & responsibilities
Executive Sponsor
Executive account oversight
2nd level escalation for any issues account issues
Sujith X, Chief Business Development Officer
Dennis Y, Technical Account Manager
Program Delivery
Account Management
1st level escalation for any issues on the account
Accountable for program and project delivery
Kelsey Z, Delivery Manager
Main point of contact for customer
Implementation and project management
Development
George W, Tech Team Lead
Solutioning and automation implementation
Daily issues and communication

## Slide 13: Governance / meetings
Forum | Role | Meeting Freequency
Steering Group | Provide guidance, approve changes to project plan and scope, monitor progress | Bi-weekly
SMEs | Provide subject matter expertise | Ad-hoc, coordinated by project leads
Project team | Deliver the project | Weekly

## Slide 14
Project plan

## Slide 15: Project calendar
*Final test – number of documents is subject to discussion
Analysis of data
Tagging of data for training set
Machine Learning implementation
Business Process with Manual Tasks
RPA with Trades DB
Jan 22 Jan 29 Feb 5 Feb 12 Feb 19 Feb 26 Mar 5 Mar 12 Mar 19 Mar 26 Apr 2
Jan 22
Feb 1
Feb 15
Feb 28
March 27
March 15
Mar 7
Feb 23
Feb 8
Jan 30
Final tests
Mar 16
Apr 3

## Slide 16: Progress till now
Started implementation of RPA:
  mail extraction bot step - done
  opening of App - done
  navigating in App - done
  checking operations in DB – in progress
Analyzed and structured data to be used for training set
Created manual task and business process for data tagging
Started qualification of SMEs and data tagging

## Slide 17: Detailed project plan

## Slide 18
Next steps

## Slide 19: Immediate priorities
Tagging of the dataset for ML model – will start full scale on Feb 22 instead of 14
Issue with receipt of emails in specified mailbox
Access (jira, git, DB for devs and bots)
Set up weekly calls – 9:30am CET on Tuesdays
First demo proposed date – March 1 (subject to the above issue fixed by the time)