## Summary
Project report – Summary End of Week 22 |  |  |  |  | Status |  | Previous Status
Summary
- All work with 3 initial processes that could be completed w/o system Y access is done. Started design and inmplementation for processes 4,5; gathering requirements for process 6. - The project is green as adjusted milestones were approved with Steering group and issues with test data fixed. Session scheduled with IT team on Tue to install production environment and move RPA server of dev environment to internal network to allow avoid MFA between systems. - Demo on May 30 raised interest with the audience so hoping to get more potential processes from other departments.
Area | Topic | Process Design | Build | Unit Test | End of UAT Go-live | End of Hypercare | Comments
Processes | Process 1: Hedge accounting | Done 04/05 | IP - target 25/05 | Target 08/06 | Target 18/06 | Target 27/06 | Blocked by no access to system Y Need to define solution for MFA
| Process 2: Reconcile bank lists | Done 04/05 | IP - target 25/05 | Target 08/06 | Target 18/06 | Target 27/06 | Blocked by no access to system Y Need to define solution for MFA
| Process 3: Rejected statements | Done 04/05 | IP - target 25/05 | Target 08/06 | Target 18/06 | Target 27/06 | Blocked by no access to system Y Need to define solution for MFA
| Process 4: Hedge Relationship | Done 04/05 | IP - target 15/06 | Target 22/06 | Target 29/06 | Target 31/08
| Process 5: Matching of auto FX transactions | IP - target 08/06 |  |  |  |  | Requirements gathered
Enablers | Access & laptops provisioning | IP - target 25/05 |  |  |  |  | Pending system Y access
| Production environment installation | Target 08/06 |  |  |  |  | Installation session scheduled for 05/06
| Internal compliance | Target 18/06

## Project Plan
ABC Business Automation
Project Plan
| W0: 04/23 |  |  |  |  | W1: 04/30 |  |  |  |  | W2: 05/07 |  |  |  |  | W3: 05/14 |  |  |  |  | W4: 05/21 |  |  |  |  | W5: 05/28 |  |  |  |  | W6: 06/04 |  |  |  |  | W7: 06/11 |  |  |  |  | W8: 06/18 |  |  |  |  | W9: 06/25 |  |  |  |  | W10: 07/02 |  |  |  |  | W11: 07/09 |  |  |  |  | W12: 07/16 |  |  |  |  | W13: 07/23 |  |  |  |  | W14: 07/30 |  |  |  |  | W15: 08/06 |  |  |  |  | W16: 08/13
ACTIVITY | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F |  | OWNER / INVOLVED
PROJECT GOVERNANCE
Define organizative structure & operating model for the project | [85 empty] | done | WF/ABC
Identify stakeholders. Define Roles & Responsabilities | [85 empty] | done | WF/ABC
Define Project Plan | [85 empty] | done | WF/ABC
Agree deliverables & formats | [86 empty] | WF/ABC
Define success criteria & measure results | [86 empty] | WF/ABC
Prepare Laptops | [85 empty] | done | ABC IT team
Set-up Laptops | [63 empty] | ` | [22 empty] | ABC IT team
Grant Acesses & Rights | [85 empty] | in progress | ABC IT team
Team Logistics (Office space, Security Accesses, etc..) | [85 empty] | done | WF/ABC
Installation of WF dev environment | [85 empty] | done | WF Installation team
Access to WF dev environment | [85 empty] | done | WF/ABC
Provision hardware for WF prod environment | [86 empty] | ABC
Installation of WF prod environment | [86 empty] | WF Installation team
Access to WF prod environment | [86 empty] | WF/ABC
MEETINGS
Kickoff | [86 empty] | WF/ABC
Weekly meetings | [86 empty] | WF/ABC
Bi-Weekly Meetings | [86 empty] | WF/ABC
Monthly steering group meetings | [86 empty] | WF/ABC
Demo/Final Presentation | [86 empty] | WF/ABC
1. RECONCILIATION OF BANK ACCOUNTS LISTS |  | Design | [13 empty] | Build | [14 empty] | Unit Test |  |  |  |  | UAT |  |  |  |  | Go-Live and Hypercare
Requirements gathering | 29 | [84 empty] | done | ABC SME
Process design | [85 empty] | done | WF Lead dev
Access to systems: Kyriba, Netsuite, Box.com |  |  |  |  | 31 | [80 empty] | in progress | ABC System owners
Validate access & connectivity to dev system |  |  |  |  | 32 | [80 empty] | delayed | WF Dev team
Configure Business Process | [85 empty] | in progress | WF Dev team
Unit testing & analyze performance metrics | [85 empty] | in progress | WF Dev team
Process documentation & user guide | [85 empty] | in progress | WF Dev team
1. UAT
Configure data for UAT | [86 empty] | WF Dev team/ABC SMEs
Conduct UAT | [86 empty] | WF Dev team/ABC SMEs
Gather Performance Metrics | [86 empty] | WF Dev team/ABC SMEs
1. PRODUCTION ROLLOUT
Provide access and users for prod system | [37 empty] | 41 | [48 empty] | WF
Validate access & connectivity to prod system | [86 empty] | ABC
Migrate code to production instance | [86 empty] | WF
Test with production data | [86 empty] | WF/ABC
Train the users/change management | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
Production rollout | [86 empty] | WF/ABC
2. FX HEDGING: 6. Hedge Accounting |  | Design |  |  |  | Build | [24 empty] | Unit Test |  |  |  |  | UAT |  |  |  |  | Go-Live and Hypercare
Requirements gathering | 50 | [84 empty] | done | ABC
Process design | [85 empty] | done | WF
Access to systems: Kyriba, Netsuite, Box.com |  |  |  |  | 52 | [80 empty] | in progress | ABC
Validate access & connectivity |  |  |  |  | 53 | [80 empty] | delayed | WF
Configure Business Process | [85 empty] | in progress | WF
Configure Manual Task | [86 empty] | WF
Unit testing & analyze performance metrics | [86 empty] | WF
Process documentation & user guide | [85 empty] | in progress | WF
2. UAT
Configure data for UAT | [86 empty] | WF/ABC
Conduct UAT | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
2. PRODUCTION ROLLOUT
Provide access and users for prod system | [37 empty] | 63 | [48 empty] | WF
Validate access & connectivity to prod system | [86 empty] | ABC
Migrate code to production instance | [86 empty] | WF
Test with production data | [86 empty] | WF/ABC
Train the users/change management | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
Production rollout | [86 empty] | WF/ABC
3. REJECTED STATEMENTS |  | Design | [13 empty] | Build | [14 empty] | Unit Test |  |  |  |  | UAT |  |  |  |  | Go-Live and Hypercare
Requirements gathering | 72 | [84 empty] | done | ABC
Process design | [85 empty] | done | WF
Access to systems: Kyriba |  |  |  |  | 74 | [80 empty] | done | ABC
Provide test data in sandbox | [14 empty] | 76 | [70 empty] | done | ABC
Validate access & connectivity |  |  |  |  | 75 | [80 empty] | done | WF
Configure Business Process | [85 empty] | in progress | WF
Configure Manual Task | [86 empty] | WF
Unit testing & analyze performance metrics | [86 empty] | WF
Process documentation & user guide | [85 empty] | in progress | WF
3. UAT
Configure data for UAT | [86 empty] | WF/ABC
Conduct UAT | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
3. PRODUCTION ROLLOUT
Provide access and users for prod system | [37 empty] | 87 | [48 empty] | WF
Validate access & connectivity to prod system | [86 empty] | ABC
Migrate code to production instance | [86 empty] | WF
Test with production data | [86 empty] | WF/ABC
Train the users/change management | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
Production rollout | [86 empty] | WF/ABC
4. FX HEDGING: 4. Hedge Relationship | [25 empty] | Design |  |  |  |  | Build | [9 empty] | Unit Test |  |  |  |  | UAT
Requirements gathering | [85 empty] | done | ABC
Process design | [86 empty] | WF
Access to systems (Kyriba) | [27 empty] | 98 | [58 empty] | ABC
Validate access & connectivity | [86 empty] | WF
Configure Business Process | [86 empty] | WF
Configure Manual Task | [86 empty] | WF
Unit testing & analyze performance metrics | [86 empty] | WF
Process documentation & user guide | [86 empty] | WF
4. UAT
Configure data for UAT | [86 empty] | WF/ABC
Conduct UAT | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
4. PRODUCTION ROLLOUT
Migrate code to production instance | [86 empty] | WF
Provide access and users for prod system | [86 empty] | ABC
Validate access & connectivity to prod system | [86 empty] | WF
Test with production data | [86 empty] | WF/ABC
Train the users/change management | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
Production rollout | [86 empty] | WF/ABC
5. PROCESS 5 | [20 empty] | Requirements | [9 empty] | Design
Requirements gathering | [85 empty] | in progress | ABC
Process design | [86 empty] | WF
Access to systems | [86 empty] | ABC
Validate access & connectivity | [86 empty] | WF
Configure Business Process | [86 empty] | WF
Configure Manual Task | [86 empty] | WF
Unit testing & analyze performance metrics | [86 empty] | WF
Process documentation & user guide | [86 empty] | WF
5. UAT
Configure data for UAT | [86 empty] | WF/ABC
Conduct UAT | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
5. PRODUCTION ROLLOUT
Migrate code to production instance | [86 empty] | WF
Provide access and users for prod system | [86 empty] | ABC
Validate access & connectivity to prod system | [86 empty] | WF
Test with production data | [86 empty] | WF/ABC
Train the users/change management | [86 empty] | WF/ABC
Gather Performance Metrics | [86 empty] | WF/ABC
Production rollout | [86 empty] | WF/ABC
Dev Install
Production Install
Assumptions:
No major new cases/exceptions are uncovered in UAT
Prod and test systems are identical
Versions of the automated prod and test systems are the same
Access is provisioned on time
Process logic does not require changes during testing
All exceptional cases are uncovered during implementation process
Test data in sandbox environment is sufficient and representative of production data
Considerations:
Frequency of production BPs: Hedging process can be launched once a day; Rejected BP can be launched once a month; Reconciliation - unknown

## Risks&Issues
Risks & Issues Log
ID | Date raised | Description | Impact (1-5) | Proba-bility (1-5) | Impact x Probability | Affects | Mitigation (inc contingencies) | Responsible | Status | Date updated
RI010 | 2018-05-23 | Need more test data to be uploaded for Process Z to continue testing | 4 | 5 | 20 | Process Z readiness for UAT and production rollout | - Ask system owner to upload new data - TBD May 28 | System XX team | Open | 2018-05-29
RI001 | 2018-04-23 | Lack of dedicated contact for IT questions slows down their resolution | 2 | 4 | 8 | Completion date and cost dragged by idle time in waiting on external system maintenance | Assign a dedicated IT contact Use Jira for technical questions | John Smith | In progress | 2018-04-23
RI008 | 2018-05-08 | System XX kicks out bot user | 1 | 1 | 1 | Minor slowdown of development process in system XX | Disable the feature if it exists - not confirmed, likely the problem was that two sessions at a time were opened | Kristina | Closed | 2018-05-10
RI013 |  |  |  |  | 0
RI014 |  |  |  |  | 0
RI015 |  |  |  |  | 0
RI016 |  |  |  |  | 0
RI017 |  |  |  |  | 0
RI018 |  |  |  |  | 0
RI019 |  |  |  |  | 0
RI020 |  |  |  |  | 0
RI021 |  |  |  |  | 0
RI022 |  |  |  |  | 0
RI023 |  |  |  |  | 0
RI024 |  |  |  |  | 0
RI025 |  |  |  |  | 0
RI026 |  |  |  |  | 0
RI027 |  |  |  |  | 0
RI028 |  |  |  |  | 0
RI029 |  |  |  |  | 0
RI030 |  |  |  |  | 0
RI031 |  |  |  |  | 0
RI032 |  |  |  |  | 0
RI033 |  |  |  |  | 0
RI034 |  |  |  |  | 0
RI035 |  |  |  |  | 0
RI036 |  |  |  |  | 0
RI037 |  |  |  |  | 0
RI038 |  |  |  |  | 0
RI039 |  |  |  |  | 0
RI040 |  |  |  |  | 0
RI041 |  |  |  |  | 0
RI042 |  |  |  |  | 0
RI043 |  |  |  |  | 0
RI044 |  |  |  |  | 0
RI045 |  |  |  |  | 0
RI046 |  |  |  |  | 0
RI047 |  |  |  |  | 0
RI048 |  |  |  |  | 0
RI049 |  |  |  |  | 0
RI050 |  |  |  |  | 0
RI051 |  |  |  |  | 0
RI052 |  |  |  |  | 0
RI053 |  |  |  |  | 0
RI054 |  |  |  |  | 0
RI055 |  |  |  |  | 0
RI056 |  |  |  |  | 0
RI057 |  |  |  |  | 0
RI058 |  |  |  |  | 0
RI059 |  |  |  |  | 0
RI060 |  |  |  |  | 0
RI061 |  |  |  |  | 0
RI062 |  |  |  |  | 0
RI063 |  |  |  |  | 0
RI064 |  |  |  |  | 0
RI065 |  |  |  |  | 0
RI066 |  |  |  |  | 0
RI067 |  |  |  |  | 0
RI068 |  |  |  |  | 0
RI069 |  |  |  |  | 0
RI070 |  |  |  |  | 0
RI071 |  |  |  |  | 0
RI072 |  |  |  |  | 0
RI073 |  |  |  |  | 0
RI074 |  |  |  |  | 0
RI075 |  |  |  |  | 0
RI076 |  |  |  |  | 0
RI077 |  |  |  |  | 0
RI078 |  |  |  |  | 0
RI079 |  |  |  |  | 0
RI080 |  |  |  |  | 0
RI081 |  |  |  |  | 0
RI082 |  |  |  |  | 0
RI083 |  |  |  |  | 0
RI084 |  |  |  |  | 0
RI085 |  |  |  |  | 0
RI086 |  |  |  |  | 0
RI087 |  |  |  |  | 0
RI088 |  |  |  |  | 0
RI089 |  |  |  |  | 0
RI090 |  |  |  |  | 0
RI091 |  |  |  |  | 0
RI092 |  |  |  |  | 0
RI093 |  |  |  |  | 0
RI094 |  |  |  |  | 0
RI095 |  |  |  |  | 0
RI096 |  |  |  |  | 0
RI097 |  |  |  |  | 0
RI098 |  |  |  |  | 0

## Delivery Plan
Overall Status: | 1/31/017
Milestones | UC1 |  |  | UC2
| Status | Actual Deadline | Planned Deadline | Status | Actual Deadline | Planned Deadline
Requirements | Completed |  |  | Completed
Dev: Release 1 | Completed |  |  | Completed
First UAT | Completed | #REF! | 2016-10-19 | Completed (Delayed) | #REF! | 2016-10-25
Last UAT | Completed (Delayed) | #REF! | 2016-11-01 | Completed (Delayed) | #REF! | 2016-11-01
GoLive | Completed (Delayed) | #REF! | 2016-11-07 | Completed (Delayed) | #REF! | 2016-11-07
Prod. Support | In progress |  |  | In progress

## Weekly monitor
Week | Sync-up | Planned Activities | Results
1 | #REF! | 1. Complete installation 2. Give access to systems 3. Conduct kickoff | 1. done 2. pending accesss to system Z 3. done
2 | #REF! | 1. Give access to system Z 2. UC1: completed dev of feature 1-3 3. UC2: completed dev of feature 1-2 | 1. done 2. UC1: completed dev of feature 1-3 3. UC2: completed dev of feature 1-2
3 | #REF! | 1. UC1: complete dev of feature 4,5 2. UC2: complete dev of feature 3,4,5 3. Demo for features 1-3 of UC1
4 | #REF!
5 | #REF!
6 | #REF!
7 | #REF!
8 | #REF!
9 | #REF!

## Releases
BP version | Major Features, Scope, Issues/Risks | Status | UAT release | Production release | Comments
UC1 v2.2 |  | Planning | 2017-02-01 | TBD
UC2 v2.2 | Excel file downloading issue | Planning |  | TBD
UC1 v2.1 |  | Planning | 2017-02-02 | 2017-03-03
UC2 v2.0 | PROD issues fixes. | Planning | 2017-02-01
Released versions
UC1 v2.0 | Excel file downloading issue "Same week as previous" fix HRMS response processing fix | Released | 2017-01-31 | TBD
UC2 v1.1 | Excel file downloading issue | Released | 2017-01-31
UC1 v1.1 |  | Released | 2017-01-20 |  | Did not happen due to missing WF accounts and RPA boxes on UAT.
UC2 v1.0 | Flexible permission notes | Released | 2017-01-18
UC1 v1.0 |  | Released | 2016-12-02

## UC1
Status | Use case 1 (UC1) |  | Client Owner: | WF Owner: | START DATE: | END DATE: | PLANNED:
2017-01-31 |  |  |  |  | 2016-10-19 | #REF! | 2016-11-07
Description Scope 1. Success Criteria and SLA targets 1. Assumptions: |  | Deliverables | Status | Owner | Duration (work days) | Actual Deadline | Planned Deadline
|  | Requirement Gathering | Completed | Customer
|  | Development of Release 1 | Completed | WF
|  | Milestone 1: UAT of Release 1 | Completed | WF+ Customer | 1 | #REF! | 2016-10-19
|  | Development of Release 2 (fixes) | Completed | WF | 3 | #REF! | 2016-10-24
|  | Milestone 2: UAT of Release 2 | Completed (Delayed) | WF+ Customer | 7 | #REF! | 2016-10-27
|  | Development of Release 3 (fixes) | Completed | WF | 1 | #REF! | 2016-10-28
|  | Milestone 3: UAT of Release 3 | Completed (Delayed) | WF+ Customer | 3 | #REF! | 2016-11-01
|  | Milestone 4: GoLive | Completed (Delayed) | WF+ Customer | 7 | #REF! | 2016-11-07
|  | Production Support | In progress | WF | 2016-11-18
Risk / Issue Item |  | Mitigation | Status | Owner | Scale (0-10) | Raised on | Updated on
|  |  | Completed |  | 9 | 2016-11-08 | 2017-01-20
|  |  | Completed |  | 8 | 2016-12-05 | 2016-12-09
|  |  | Completed |  | 5 | 2016-11-08 | 2016-11-21
Formulas:
END DATE: = WORKDAY(H3-1,[START DATE:],#REF!)
END DATE: = WORKDAY([END DATE:, row above],[START DATE:],#REF!)
Note on H10: Original 3 days
Note on H12: Original 2 days
Note on E14: Siarhei Kauryhin: See Releases tab.

## UC2
Status | Use case 2 (UC2) |  | Client Owner: | WF Owner: | START DATE: | END DATE: | PLANNED:
2017-01-31 |  |  |  |  | 2016-10-21 | #REF! | 2016-11-07
Description Scope 1. Success Criteria and SLA targets 1. Assumptions: |  | Deliverables | Status | Owner | Duration (work days) | Actual Deadline | Planned Deadline
|  | Requirement Gathering | Completed | Customer
|  | Development of Release 1 | Completed | WF
|  | Milestone 1: UAT of Release 1 | Completed (Delayed) | WF+ Customer | 9 | #REF! | 2016-10-25 | `
|  | Development of Release 2 (fixes) | Completed | WF | 1 | #REF! | 2016-10-26
|  | Milestone 2: UAT of Release 2 | Completed (Delayed) | WF+ Customer | 5 | #REF! | 2016-10-28
|  | Development of Release 2 (fixes) | Completed | WF | 1 | #REF! | 2016-10-31
|  | Milestone 3: UAT of Release 3.0 | Completed (Delayed) | WF+ Customer | 8 | #REF! | 2016-11-01
|  | Milestone 3: GoLive | Completed (Delayed) | WF+ Customer | 3 | #REF! | 2016-11-07
|  | Production Support | In progress | WF | 2016-11-30
Risk / Issue Item |  | Mitigation | Status | Owner | Scale (0-10) | Raised on | Updated on
|  |  | In-progress | Citi | 9 | 2016-11-08 | 2017-01-24
|  |  | Completed | Citi | 10 | 2016-11-08 | 2016-12-02
|  |  | Completed | Citi | 10 | 2016-11-01 | 2016-11-25
Formulas:
END DATE: = WORKDAY(H3-1,[START DATE:],#REF!)
END DATE: = WORKDAY([END DATE:, row above],[START DATE:],#REF!)
Note on H8: Original duration was 3 days
Note on H10: Originally planned 2 days
Note on E14: Siarhei Kauryhin: See Releases tab.

## UC1-Features
Corrective Actions
Epic | Feature | Details | Automation Value (0-3) | Effort (0-3) | Priority (0-3) | Release | JIRA Status | Ops Sign-off
Epic 1 | Feature 1 |  |  | 0 | 3 | 1 | Done | Confirmed
Epic 1 | Feature 2 | Validate values after Save button is pressed (Error Message handling). |  | 3 | 3 | 3 | Done | Confirmed
Epic 1 | Feature 3 | All exceptions go to Tier 2 |  | 1 | 3 | 3.4 | Done | Confirmed
Epic 1 | Feature 4 | Set "Open-Working" status for all exception cases. |  | 1 | 3 | 3.4 | Done | Confirmed
Epic 1 | Feature 5 | Check Notes for Permission Note with Employee(s). |  | 1 | 3 | 3.5 | Done | Confirmed
Epic 2 | Feature 6 |  |  | 2 |  |  | On Hold
Epic 2 | Feature 7 | Extract data from the GRID of plain text. |  | 3 |  |  | On Hold
Epic 2 | Feature 8 | 1) Add new Month to Date section, 2) Break out metrics by BPs, 3) Calculate SLA %, 4) Create Excel detailed report, 5) Change subject to "Daily RPA Report", 6) Add time to timestamp in DataStore. |  | 2 | 3 | 2.1 (RS) | Done | Not Checked

## UC2-Features
Connect One
Epic | Feature | Details | Automation Value (0-3) | Effort (0-3) | Priority (0-3) | Version | JIRA Status | Ops Sign-off
Epic 1 | Feature 1 |  |  | 0 | 3 | 1 | Done | Confirmed
Epic 1 | Feature 2 | Validate values after Save button is pressed (Error Message handling). |  | 0 | 3 | 1 | Done | Confirmed
Epic 1 | Feature 3 | All exceptions go to Tier 2 |  | 0 | 3 | 1 | Done | Confirmed
Epic 1 | Feature 4 | Set "Open-Working" status for all exception cases. |  | 1 | 3 | 2 | Done | Confirmed
Epic 1 | Feature 5 | Check Notes for Permission Note with Employee(s). |  | 2 | 3 | 2 | Done | Confirmed
Epic 2 | Feature 6 |  |  | 1 | 3 | 2 | Done | Confirmed
Epic 2 | Feature 7 | Extract data from the GRID of plain text. |  | 2 | 3 | 2 | Done | Confirmed
Epic 2 | Feature 8 |  |  | 3 | 3 | 2 | Done | Confirmed