## Status
DBL Status | Project tracker |  | DB Owner: | WF Owner: | START DATE: | END DATE:
2016-07-28 |  |  |  |  | 2016-07-07 | 2016-08-05
Description Scope Success Criteria and KPIs |  | Action Items | Status | Owner | Duration (work days) | Deadline
|  |  | Completed | WF | 4 | 2016-07-13
|  | Milestone 1: | Completed | WF+Client | 3 | 2016-07-18
|  |  | In-progress | WF | 8 | 2016-07-28
|  | Milestone 2: | Not started | WF+Client | 6 | 2016-08-05
Progress this week: | 0
Activities next week: | 0
Risk / Issue Item |  | Mitigation | Status | Owner | Scale (0-10) | Updated
|  |  | Completed |  | 6 | 2016-07-18
|  |  | In-progress |  | 9 | 2016-07-21
Formulas:
END DATE: = WORKDAY(H3,[START DATE:],"7/4/2016")
END DATE: = WORKDAY([END DATE:, row above],[START DATE:],"7/4/2016")

## Weekly monitor
Week | Sync-up | Activities | Results
0 | 2016-07-07
1 | 2016-07-14
2 | 2016-07-21
3 | 2016-07-28
4 | 2016-08-04
5 | 2016-08-11
Include accountability, responsibility and ETA within the descriptions that you provide for activities and results
Formulas:
Sync-up = [Sync-up, row above]+7

## Overall RPA Transition HLP
|  |  | Jul'16 |  |  |  | Aug'16 |  |  |  | Sep'16 |  |  |  | Oct'16 |  |  |  | Nov'16 |  |  |  |  | Dec'16 |  |  |  | Jan'17 |  |  |  |  | Feb'17 |  |  |  | Mar'17 |  |  |  | Apr'17
| Bot Name | FTEs | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29 | 2016-09-05 | 2016-09-12 | 2016-09-19 | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08
Environment Setup
Bot 1 Development | Payment Attachment
Bot 2 Development | Uber
Bot 4 Development | Follow Up
Bot 5 Development | Case Loading
Bot 6 Development | 3 Strike Rule
Bot 7 Development | Auto Acknowledgement
Bot 8 Development | Update Notes
Bot 9 Development | Resolution Notes
Bot 10 Development | Correspondence
Bot 11 Development | Citi Direct Update
Bot 12 Development | Create Payment Instruct
Bot 13 Development | Update POR
Group 1 upgrade
Group 2 upgrade
Group 3 upgrade
Group 4 upgrade
People ramp-down | [20 empty] | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
No. of Robots ( Unique ) | [20 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 8 | 8 | 8 | 12 | 12
[16 empty] | Activity |  |  |  |  | Legend |  | Team
Bots Grouping - Total 16 Instances | [15 empty] | Code Freeze | [6 empty] | TNT
Gr 1 - Payment Attachment - 03 Uber FTE 01 | [15 empty] | Requirement Analysis | [6 empty] | TNT / OPM
Gr 2 - Case Loading BOT - 01 Follow up Reminder - 01 3 Strike Rule - 01 Auto Acknowledgment -01 | [15 empty] | Requirement Sign Off | [6 empty] | TNT/OPM
Gr 3 - Update Notes - 01 Resolution Notes/Closure -03 | [15 empty] | Development | [6 empty] | TNT
Gr 4 - Correspondence - 01 Citi Direct update - 01 Create Payment Instruction - 01 Updating POR - 01 | [15 empty] | Process Base Lining | [6 empty] | OPM
[16 empty] | UAT And Sign Off | [6 empty] | TNT/Ops
[16 empty] | Go Live | [6 empty] | TNT / Ops
[16 empty] | Volume ramp up | [6 empty] | Ops / OPM
[16 empty] | Impact Analysis | [6 empty] | Ops / OPM
[16 empty] | FTE Ramp Down | [6 empty] | Ops / OPM
V`
V`
V`
V`
V`
V`
V`
V`

## Risk & Issue Log
Project Name Place Holder - Project Transition Risk & Issue Log (Overall Project)
Sr. # | Audience | Item | Category | Potential Impact | Problem Description | Type (Owner/Category) | Target Date | Closure Date | Status | Remarks
In pogress
Solved
Need priority
Parked
Special (low priority)